## Overview
MyRX Launch Checklist — Overview
Six-phase checklist for going live with the coach platform v1 + B2C tiers. Each phase has its own sheet. Work through phases in order — Phase N+1 assumes Phase N is mostly green. Owner column: 'M' = Motaz (user), 'C' = Claude (assistant), 'L' = Lawyer (if engaged). Status: blank → Pending → In Progress → Done. Or Skip (intentional pass) / Blocked (dependency).
Phase | Sheet name | Focus
Phase 1 — T-30 days | Phase 1 — T-30 days | Foundation (legal sign-off, infra hardening, app store enrollment, payment go-live setup)
Phase 2 — T-7 days | Phase 2 — T-7 days | Final QA pass + mobile submissions (allow 1-2 weeks for App Store, 2-3 days for Play)
Phase 3 — Launch day | Phase 3 — Launch day | Deploy sequence + announce (1-hr active monitoring)
Phase 4 — T+1 day | Phase 4 — T+1 day | Day-after metrics + support inbox triage
Phase 5 — T+7 days | Phase 5 — T+7 days | Week-one retrospective + bug triage from first reports
Phase 6 — T+30 days | Phase 6 — T+30 days | First-month cost review + metrics + vendor plan adjustments

## Phase 1 — T-30 days
Phase 1 — T-30 days
Foundation work. Most items are blocking — incomplete legal/payments/app-store items will delay launch.
Category | Item | Why it matters | Owner | Status | Notes
Legal | All 9 legal docs reviewed for accuracy | Stale prose = liability. Esp. Privacy + Refund. | M+L | Pending | Files in docs/legal/*.docx. Self-review at minimum; lawyer review if scope changes (B2C launch).
Legal | GDPR data export endpoint works for any user | Required if any EU user. Privacy Policy promises it. | C | Pending | Test by creating a throwaway account → request data export → verify all fields exported.
Legal | Data deletion (hard delete) flow tested | Right to be forgotten — GDPR Article 17. | C | Pending | Already implemented (task #138). Re-test end-to-end before launch.
Legal | Cookie banner verified on every marketing page | Cookie Policy promises consent before non-essential cookies fire. | M | Pending | Inspect each landing page: cookie banner appears, declining works, analytics doesn't fire.
Legal | DPA download link works from public site | EU coaches need to download + countersign for GDPR compliance. | M | Pending | Currently the DPA is at /dpa as a webpage. Add a download-as-PDF link if a coach asks for a signable version.
Legal | Coach Agreement checkbox enforced at signup | Without it, coaches haven't legally accepted ToS — no liability shield. | C | Done | Already shipped (task #171). Just confirm it still works after any signup-flow changes.
Tech | Cloudflare Pages production stable for 7+ days no incident | Baseline reliability check before promoting to launch. | C | Pending | Watch the production deploy at myrxfit.com. Track build success rate, any 5xx spikes.
Tech | Supabase production tier capacity check | Free tier: 500MB DB + 1GB storage + 2GB bandwidth. Likely fine for launch but check. | M+C | Pending | Dashboard → Project Settings → Usage. If close to limits, upgrade to Pro ($25/mo).
Tech | Backup strategy verified | Need point-in-time recovery enabled OR weekly DB dumps. | C | Pending | Supabase Pro includes PITR. Free tier: no built-in backups → need pg_dump cron.
Tech | Mobile dev-client APK rebuilt against latest source | Catch any native-module breakage before App Store submission. | C | Pending | From /mobile: npx expo run:android (and equivalent run:ios when Apple Dev approved).
App Store | Apple Developer Program enrolled + verified | Without it, can't submit to App Store. | M | Pending | $99/yr. LLC verification can take 1-4 weeks.
App Store | Google Play Developer Account enrolled | Without it, can't submit to Play Store. | M | Pending | $25 one-time.
App Store | Replace web /app placeholder with full download landing page | Right now /app is a holding page (text only — 'MyRX is mobile-first … coming soon'). Once iOS + Android apps ship, swap to the full launch page. | M+C | Pending | File: web/src/pages/DownloadAppPlaceholder.jsx. Component is intentionally simple right now; everything below is what gets added at app-launch time.
App Store | /app page: App Store badge + click-through | Apple's official 'Download on the App Store' SVG badge. Click → opens App Store page for MyRX. | M+C | Pending | Apple brand guidelines: https://developer.apple.com/app-store/marketing/guidelines/ — use the official asset, don't redraw.
App Store | /app page: Play Store badge + click-through | Google's official 'Get it on Google Play' SVG badge. Click → opens Play Store page for MyRX. | M+C | Pending | Google brand guidelines: https://play.google.com/intl/en_us/badges/ — use the official asset.
App Store | /app page: QR code that deep-links to the install URL | QR code visible to users on desktop. Scan with phone → opens whichever store matches their OS (App Store for iOS, Play Store for Android). Use a service like qrserver.com or generate at build time. | M+C | Pending | Should be a smart link that detects OS — or two QR codes side by side (iOS / Android).
App Store | /app page: hero copy and screenshots | Replace the 'coming soon' card with real product framing — 1 hero screenshot of the app + 3 supporting screenshots showing strength / cardio / coach view. | M | Pending | Designer pass or simple grid; Apple/Google store screenshots can be reused.
App Store | /app page: invite-token deep link (when arriving via /coach/accept-invite?token=...) | If the user arrived because they clicked an email invite link from desktop, the QR code / smart link must include the invite token so the mobile app's signup flow can pick it up. Universal Link / App Link on the mobile side handles this — page just has to pass the token through to the install URL. | M+C | Pending | Currently /coach/accept-invite captures the token in URL. /app needs to read URL params and append to install link.
App Store | /app page: support email (team@myrxfit.com) visible | If a user has trouble installing / signing in, give them a way to reach support. | M | Pending | Footer link is fine; don't make it loud.
App Store | /app page: 'sign in here' link to /for-coaches for misrouted coaches/admins | Already present in the placeholder — confirm it stays in the full launch version. Coach/admin who somehow lands on /app needs an obvious way back to the coach sign-in. | C | Done | Already in the placeholder. Just preserve when redesigning.
App Store | /app page: legal links footer (Privacy, ToS) | Footer or bottom-of-page links. Required for App Store + Google Play app-marketing-page review. | M+C | Pending | Standard legal-footer pattern; mirror what /for-coaches has.
App Store | /app page: hreflang / SEO meta if marketing internationally | If the app launches in non-English markets, the page needs translated copy + hreflang tags. Defer if launch is English-only initially. | M | Pending | Skip for English-only launch.
App Store | App icons (all required sizes for iOS + Android) | Both stores reject submissions with missing/wrong-size icons. | M+C | Pending | iOS: 1024x1024 marketing + 180/167/152/120 in-app. Android: 512x512 store + 192 launcher.
App Store | Screenshots for store listings (5 minimum per platform) | Conversion lever — best screenshots have the value prop in the first frame. | M | Pending | iOS: 6.7" + 6.5" + 5.5" sizes. Android: phone + 7" tablet + 10" tablet.
App Store | Store listing text written (description, keywords, what's new) | SEO inside the store. Determines who finds you. | M | Pending | Keywords matter most on Apple. Description matters most on Google.
App Store | Production keystore SHA256 added to assetlinks.json | Magic-link emails open in app (not browser) on Android. Currently only debug key registered. | C | Pending | web/public/.well-known/assetlinks.json — add prod SHA256 fingerprint, redeploy web.
App Store | TestFlight internal testing — 1 full week with 3+ testers | Catches bugs that don't surface on a single device. | M+C | Pending | Recruit 2-3 willing friends. Pre-launch is the safest QA window.
App Store | Google Play Internal Testing — 1 full week with 3+ testers | Same as above for Android. | M+C | Pending | Internal testing track is fastest; can iterate same-day on Play.
Payments | Stripe Live mode activated | Test keys can't accept real money. Live keys gated on business verification. | M | Pending | Dashboard → Activate Account. Provide: EIN, bank account for payouts, ID.
Payments | Stripe Live webhook endpoint configured | Without this, subscription events (cancel, renew, refund) don't propagate to your DB. | C | Pending | Stripe → Webhooks → Add endpoint → /functions/v1/stripe-webhook?source=coach_subs. Copy signing secret to STRIPE_WEBHOOK_SECRET_LIVE in Supabase Edge Function secrets.
Payments | Test full purchase flow in Stripe Live mode | Use real card with $0.50 charge → confirm DB updates + email sent + refund flow works. | C | Pending | Refund the test charge afterwards. Document any flow gaps.
Payments | Refund-policy response SLA committed | billing@myrxfit.com needs to respond to refund requests within X hours per Refund Policy. | M | Pending | Document the SLA internally. Even '24 hours' is fine if you stick to it.
Email | Mail-tester.com score ≥ 9/10 | Comprehensive deliverability check before launch. | C | Pending | Send test from each outbound path to the temp address mail-tester gives. Aim for 10/10.
Email | DMARC at p=reject (final state) | Catches end of the 4-week ramp. Sequenced in docs/reminders.xlsx. | C | Pending | Schedule: pct=100 around Jun 10, reject around Jun 24.
Email | Transactional templates reviewed for tone + branding | Coach invite, OTP, password reset all currently functional but generic. | M+C | Pending | If a designer is engaged, get them to skin the templates.
Monitoring | Cloudflare alert on 5xx spike | Catches regressions before users report them. | C | Pending | Cloudflare → Notifications → Add → HTTP 5xx Rate threshold.
Monitoring | Supabase log alerts on auth errors | Spike in failed signups = something broken in OTP/email chain. | C | Pending | Supabase doesn't have native alerts; pipe logs to a third-party (Sentry / BetterStack) OR check daily.
Monitoring | Stripe webhook failure alert | Failed webhooks = silent subscription-state drift between Stripe + your DB. | C | Pending | Stripe → Webhooks → endpoint → Alert on failure threshold.
Monitoring | Frontend error tracking enabled (Sentry or similar) | Without it, JS errors in production are invisible. | M+C | Pending | Sentry free tier covers small launches. Wire into web + mobile.
Support | support@myrxfit.com tested + auto-reply set up | First impression for users who hit issues. | M | Pending | Set auto-reply in Zoho: 'Got your message, replying within X hours.'
Support | Customer support response process documented | Internal doc so you (or future hires) know what to do when X email lands. | M | Pending | Simple wiki page is fine. Categorize: billing / bug / feature request / abuse.
Marketing | Landing page CTAs work + analytics fires | Conversion measurement is impossible without working analytics. | M+C | Pending | Test from incognito: click each CTA, verify the funnel event fires (if analytics added).
Marketing | Pricing page accurate + matches Stripe products | Mismatched prices = chargeback risk + bad reviews. | M | Pending | Cross-check web/src/pages/Pricing.jsx + Stripe Product IDs in .env.example.
Marketing | SEO basics: title tags, meta descriptions, OG images | Determines what shows up in Google + social shares. | M+C | Pending | Check every public page has unique <title> and <meta description>.
Marketing | Domain transferred to Cloudflare Registrar (if Jul 6 has passed) | Saves ~$10/yr + simpler vendor relationship. | M+C | Pending | Triggered by docs/reminders.xlsx Jul 6 deadline. Optional — can defer.

## Phase 2 — T-7 days
Phase 2 — T-7 days
Final QA + lock-down. After this phase, no new features until post-launch.
Category | Item | Why it matters | Owner | Status | Notes
Tech | Full regression test on every authed surface | Catches anything broken since Phase 1 lock. | M+C | Pending | Walk through: signup → onboarding → log strength → log cardio → log food → settings → delete account.
Tech | Synthetic load test (3-5 concurrent users) | Cheap sanity check that Supabase doesn't choke on the launch spike. | C | Pending | Even just opening 5 incognito windows + doing things simultaneously catches obvious bottlenecks.
Email | Send each of 5 templates: signup, password reset, coach invite, OTP, magic link | Confirm every transactional path works AND lands in inbox (not spam). | M+C | Pending | Use a fresh Gmail + Hotmail + Yahoo account for each. Check all 3 inboxes for each template.
Email | DMARC final-state confirmed (p=reject) | Locks down spoofing risk before launch traffic. | C | Pending | Final step in the ramp. See docs/reminders.xlsx → Jun 24 deadline.
Payments | Stripe live: full purchase + cancel + refund flow tested | Production payment flow has its own edge cases (3D Secure, declined cards). | M+C | Pending | Test with a real card (small charge → refund afterwards). NOT test cards on live mode.
App Store | iOS App Store submission lodged | Apple review takes 1-2 weeks typically. Submit at T-7 to land before T-0. | M+C | Pending | Xcode Archive → Distribute → App Store Connect → Submit for Review.
App Store | Google Play submission lodged | Play review is faster (~2-3 days). Submit at T-7 = comfortable buffer. | M+C | Pending | Play Console → Production track → upload AAB → roll out.
Monitoring | All alert channels tested (Slack/email/SMS) | Alerts only useful if they actually reach you. | M | Pending | Trigger a fake alert from each system → confirm notification arrives.
Comms | Launch announcement copy drafted (email + social) | Drafted now so you're not writing it under launch-day pressure. | M | Pending | Have 2-3 variants ready. Soft-launch tone vs. excited tone.
Comms | FAQ page or help center seeded with top expected questions | Deflects support load. Top FAQs: pricing, how to cancel, what data you store, refund process. | M | Pending | Doesn't need to be elaborate. 10-15 Q&As is plenty for launch.

## Phase 3 — Launch day
Phase 3 — Launch day
Go-live execution. Sequence matters: payments live BEFORE announce email.
Category | Item | Why it matters | Owner | Status | Notes
Deploy | Switch STRIPE_MODE from test → live in production env vars | Real payments start flowing. Test mode payments fail silently in production. | C | Pending | Stripe edge function reads STRIPE_MODE. Confirmed live via a $0.50 test charge.
Deploy | Cloudflare Pages production on latest source commit | Run wrangler pages deploy web/dist before announce email goes out. | C | Pending | Verify with: curl -s https://myrxfit.com/ ¦ grep -oE 'index-[^"]+\.js' vs local dist/.
App Store | iOS app release approved + published (manual or auto-release) | Push the button to make it discoverable in App Store search. | M | Pending | Apple sometimes auto-releases on approval, sometimes waits for manual push.
App Store | Google Play release rolled out to 100% production track | Same for Android. | M | Pending | Play Console → Production → Manage release → publish.
Announce | Launch email sent to mailing list (if exists) | Largest traffic spike of the day, typically. | M | Pending | Send from team@myrxfit.com via SendGrid (so it's DKIM-signed).
Announce | Social media posts published (LinkedIn, X, Instagram) | Multi-channel for max reach. | M | Pending | Pre-scheduled at T-0 morning, or live-posted by user.
Monitoring | 1-hour active live monitoring window after announce | First-hour traffic spike is where things break. | M+C | Pending | Watch CF Pages dashboard + Supabase logs + Stripe events simultaneously.
Support | Inbox actively monitored (1-hour SLA day-of) | First impression matters. Quick responses on launch day pay back for months. | M | Pending | Plan for: ~5-20 emails depending on launch reach.

## Phase 4 — T+1 day
Phase 4 — T+1 day
Day-after triage. Catch any silent regressions before they snowball.
Category | Item | Why it matters | Owner | Status | Notes
Monitoring | Check error rate vs baseline | Any 5xx spike, JS errors, failed signups need same-day fix. | C | Pending | Compare to Phase 1 baseline.
Monitoring | Check signup conversion rate | If conversion < 30%, something's broken in the funnel. | M+C | Pending | Analytics → funnel report → drop-off points.
Payments | Check payment success rate | Stripe Dashboard → Payments → failed declined %. | M | Pending | Some decline rate is normal. >5% suggests 3D Secure issue or pricing-page UX problem.
Email | Check DMARC aggregate report inbox | First post-launch report shows whether real-world spoof attempts exist + whether legit mail still passes. | C | Pending | dmarc_rua@onsecureserver.net → forwarded summaries.
Support | Respond to every email in inbox | Day-1 response time signals how serious you are. Aim for sub-12-hour. | M | Pending | Categorize as you respond: bug / billing / feature / abuse.

## Phase 5 — T+7 days
Phase 5 — T+7 days
Week-one stabilization + customer outreach.
Category | Item | Why it matters | Owner | Status | Notes
Retro | What worked / what didn't — written retro | Lessons compound. Capture them while fresh. | M+C | Pending | 30 min, free-form. Save to docs/retros/T+7-launch-retro.md or similar.
Tech | Triage bugs reported in first week | Triage matters more than fixing everything. Categorize by severity. | M+C | Pending | Critical = data loss / payment broken. High = blocks signup. Medium = minor flow issue. Low = cosmetic.
Marketing | Adjust marketing based on actual traffic data | What channels delivered? What didn't? Rebalance spend. | M | Pending | Analytics → acquisition → channel report.
Comms | Personal thank-you email to first 10-20 signups | Highest-leverage customer-success move on a small launch. | M | Pending | Manual send from team@myrxfit.com. Pure relationship-building.

## Phase 6 — T+30 days
Phase 6 — T+30 days
First-month review. Set the rhythm for monthly-cycle ops going forward.
Category | Item | Why it matters | Owner | Status | Notes
Finance | Vendor cost review | First-month bills land — surprises here can blow runway. | M+C | Pending | Supabase, Cloudflare egress, SendGrid, Twilio, Stripe processing. Compare to forecast.
Tech | Vendor capacity check — any nearing limits? | Supabase free tier limits hit silently. Cloudflare has bandwidth allowances. | C | Pending | If any vendor at >70% capacity, plan upgrade for month 2.
Finance | First quarterly metrics review | MRR, ARPU, churn, LTV, CAC. Even rough numbers are useful. | M+C | Pending | Don't over-engineer the dashboard. Spreadsheet is fine for the first review.
Marketing | Iterate on signup funnel based on 30 days of data | Whatever the lowest-converting step is gets the next month's attention. | M+C | Pending | Common offenders: pricing page, onboarding length, email confirmation friction.
Comms | Customer feedback loop — survey or interviews | 30 days of usage is enough for users to have opinions. | M | Pending | 5-question survey OR 5 30-min user interviews. Both valuable; interviews give more depth.
Legal | Quarterly legal docs review (per docs/reminders.xlsx) | Catches stale prices, vendor names, contact addresses. | M | Pending | Walk through docs/legal/*.docx for accuracy.