## Date-Specific Deadlines
Date-Specific Deadlines
Drop-dead dates. Days remaining auto-counts down vs TODAY(). After each item lands, change its Status cell to 'Done'.
Date | Days Remaining | What to do | How | Status | Notes
2026-06-10 |  | DMARC ramp Step 2: bump pct from 25 → 100 | Run CF API PUT with content `v=DMARC1; p=quarantine; pct=100; adkim=r; aspf=r; rua=mailto:dmarc_rua@onsecureserver.net;`. ~2 weeks after Step 1 (May 27). | Pending | Pre-check: review any DMARC aggregate reports for unexpected fails.
2026-06-24 |  | DMARC ramp Step 3: flip to p=reject (final state) | CF API PUT with content `v=DMARC1; p=reject; adkim=r; aspf=r; rua=mailto:dmarc_rua@onsecureserver.net;`. ~2 weeks after Step 2. | Pending | Final hardened state. Spoofed mail bounces, never reaches inbox. Don't proceed if any quarantine-period complaints surfaced.
2026-07-06 |  | Initiate myrxfit.com transfer from GoDaddy → Cloudflare Registrar | Follow 8-step walkthrough in docs/vendors.xlsx → 'Domain Transfer Countdown' sheet. Saves ~$10/yr. | Pending | ICANN 60-day lock expires this date per GoDaddy's confirmation screen. Zero downtime — DNS already at Cloudflare.
2026-07-25 |  | SendGrid Trial ends — pick paid plan or alternative | Choices: SendGrid Essentials ($20/mo, 50k sends), Pro ($90/mo, 100k), or migrate outbound to AWS SES (~$0.10 per 1k). Decide based on actual coach invite + OTP volume by then. | Pending | Without action: outbound app email stops. Set calendar 5 days before.
2027-05-18 |  | Zoho Mail Lite annual renewal ($12) | Auto-renews if card on file. Otherwise: Mail Admin → Subscription → Renew. | Pending | Could upgrade to Workplace if user count grows past 1 (currently solo).
Formulas:
Days Remaining = MAX(0,[Date]-TODAY())

## Event-Triggered Actions
Event-Triggered Actions
"When X happens, do Y." These aren't dated — they fire when their trigger occurs. Mark 'Done' once the trigger has fired AND the action completed.
Trigger (when…) | Then (do…) | Reference | Status | Notes
Apple Developer Program enrollment approved | Complete iOS reflection checklist before first TestFlight build | CLAUDE.md → 'iOS reflection checklist' section | Watch | $99/yr. Apple verification can take 1-4 weeks for LLC.
Strava API app registered (instant, no approval) | Build Strava integration (OAuth2 + REST) | CLAUDE.md → 'Strava' build order #1 | Watch | First integration to build because no approval delay.
Fitbit Personal-tier app registered (instant) | Build Fitbit integration (OAuth2 + Web API) | CLAUDE.md → 'Fitbit Web API' build order #2 | Watch | Personal tier rate-limited; production tier needs separate approval.
Apple Developer Program active → HealthKit entitlement | Build Apple HealthKit integration (mirror Samsung Health Data SDK architecture) | CLAUDE.md → 'Apple HealthKit' build order #3 | Watch | Native iOS framework. Requires com.apple.developer.healthkit entitlement.
Garmin Health API approval received (~2-4 wks) | Build Garmin integration (OAuth1.0a + webhooks) | CLAUDE.md → 'Garmin Health API' build order #5 | Watch | Apply at https://developer.garmin.com — fill application from docs/integrations/developer-program-applications.md.
Whoop API v1 approval received (~1-2 wks) | Build Whoop integration (OAuth2 + webhooks) | CLAUDE.md → 'Whoop API v1' build order #6 | Watch | Apply at https://developer.whoop.com.
Polar AccessLink approval received (~1-2 wks) | Build Polar integration (OAuth2) | CLAUDE.md → 'Polar AccessLink' build order #7 | Watch | Apply via Polar Business team.
A client reports 'I never got your reply' | Pause DMARC ramp progression. Check SendGrid Activity Feed + Zoho's outgoing log for that recipient. Inspect headers if available. If a legitimate path is failing DMARC, find root cause before continuing the ramp. | SendGrid: https://app.sendgrid.com/email_activity Zoho: Sent folder → original message → View Source | Watch | Most likely cause if it happens: a vendor we forgot is still sending mail as @myrxfit.com unaligned. Investigate before tightening DMARC further.
Before swapping email vendor / changing outbound infrastructure | Send test from EACH outbound path → verify dkim=pass + dmarc=pass in recipient headers, BEFORE making the change permanent. Update docs/vendors.xlsx + CLAUDE.md email section in same turn. | Existing pattern: Test 1/2/3 emails earlier this session. | Watch | Saves the kind of 4-hour Resend-to-SendGrid debug saga that birthed this whole reminders file.
When CLAUDE.md exceeds ~5000 lines | Extract stable locked sections (Animation Patterns, Wearable scars, etc.) into /docs/*.md reference files and link from CLAUDE.md. | Maintainability — context window costs scale with file size. | Watch | Currently the file is large but locked sections aren't actually being re-read by every Claude turn — they're being summarized.
Resend account dormant >60 days | Resend auto-deactivates free-tier accounts. Confirm closure at resend.com → Settings → Delete Account for hygiene. | Resend was removed from pipeline on 2026-05-27 but the account itself wasn't closed. | Watch | Low priority but cleaner to officially close.
First time setting up production Stripe webhook | Change STRIPE_WEBHOOK_SECRET_LIVE in Supabase Edge Function secrets. Test with Stripe CLI: `stripe listen --forward-to https://xtxzfhoxyyrlxslgzvty.supabase.co/functions/v1/stripe-webhook?source=coach_subs` | .env.example documents the secret name | Watch | Currently TEST mode only. Live keys not pulled.
Before Play Store production release | Add production keystore SHA256 to public/.well-known/assetlinks.json so Android App Links deep-linking works. | Currently only debug keystore SHA256 is registered. | Watch | If you skip this, magic-link emails open the browser instead of the mobile app on Android.

## Recurring Tasks
Recurring Tasks
Tasks that repeat on a schedule. Update 'Last Done' each time you complete one — 'Next Due' auto-derives from it.
Cadence | What to do | Why | Last Done | Next Due (auto)
Monthly (1st week) | Review DMARC aggregate reports forwarded to dmarc_rua@onsecureserver.net | Catches new senders or alignment regressions before they become real problems
Quarterly | Rotate Cloudflare + SendGrid + Twilio API keys | Security hygiene — limits blast radius if a credential leaks (incl. from chat transcripts)
Quarterly | Review legal docs in docs/legal/*.docx for accuracy (prices, vendor names, contact addresses) | Stale legal text is a liability — esp. Privacy Policy + Refund Policy
Yearly | Review docs/vendors.xlsx for stale entries, cost optimization, plan upgrades | Catches abandoned tools still billing, opportunities to consolidate
Yearly (around Sep) | Apple Developer Program renewal ($99) | iOS app distribution stops if not renewed
Per mobile release | Bump app version in mobile/app.json + run iOS reflection checklist before TestFlight | Apple rejects unchanged versions; reflection catches platform-specific bugs |  | n/a (per-event)

## How To Use This File
How To Use This File
Status conventions
Pending | Hasn't happened yet but on the calendar (amber background)
Done | Action completed (green background) — leave the row for history
Snoozed | Intentionally pushed (blue background) — update Notes to say why
Overdue | Date passed without action (red background) — fix or revisit
Watch | Event-triggered, hasn't fired yet (indigo background) — passive monitoring
Updating dates
Days Remaining | Auto-computed via =MAX(0, dateCell - TODAY()). Don't overwrite the formula.
Next Due (recurring sheet) | Auto-derived from Last Done + cadence. Update Last Done after completing the task and Next Due updates itself.
Date formatting | All date cells are yyyy-mm-dd. Excel auto-recognizes them as dates for the formulas.
Regenerating this file
Source | scripts/build_reminders_xlsx.py — Python + openpyxl
Command | From repo root: python scripts/build_reminders_xlsx.py
Note | Regenerating wipes any manual edits to status cells. If you've marked things Done that aren't in the source, copy your overrides into the script first, then regenerate.
Cross-references
docs/vendors.xlsx | Vendor inventory — referenced by GoDaddy unlock + Zoho renewal items
docs/legal/*.docx | Legal docs — referenced by quarterly review item
CLAUDE.md | Project bible — referenced by iOS, integrations, and dev-environment items